## Sheet1
# | Taks | Description | Acceptance Criteria | Owner | Start date | End Date | NoOfDays | Remarks
1 | Create common working place | Github/Drive | 1. Folder format to save data 2. Github Repo 3. Shared Drive folder | Umesh |  | 3rd Dec
2 | Interim report template |  |  | Ajay
2 | EDA |  | 1. Distribution of different classes (Opacity, no opacity and no opacity - not normal) 2. Find the position (in lungs) where the majority of opacities are observed 3. Outliers <NOT LIMITED TO ABOVE POINTS> | Manoj/Sumeeth |  | 5th Dec | 2 | 5th Dec Discussion at 8PM
3 | Pre-processing |  | Handling outliers Data balancing (data augmentation if required) | Umesh/Naveen |  |  |  | 5th Dec Discussion at 8PM
4 | Preparing the data for model
1 | Exploring differing backbone networkds (models) | [5 empty] | 3
2 | Input data preperation for mode
3 | Building model